## Blad1
weeknr | [37 empty] | weeknr | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
| 2020-11-01 |  |  | dec |  |  |  |  | 2021-01-01 |  |  |  | feb |  |  |  | mrt |  |  |  |  | april |  |  |  | mei |  |  |  | juni |  |  |  |  | juli |  |  |  | 30: augustus; 34: september; 39: oktober
| Sprint 0 | ​ |  | ​ | Sprint 1 | ​ | oud & nieuw |  |  | Sprint 2 |  |  |  | Improvement | Sprint 3 |  |  |  | improvement | Sprint 4 |  |  |  | Improvement | Sprint 5 |  |  |  | Improvement | Sprint 6 |  |  |  | Improvement | Sprint 7 |  |  |  | 30: Sprint 8; 33: Sprint 9; 35: Sprint 10; 37: Sprint 11; 39: Sprint 12; 41: Sprint 13
WEEK VAN | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 15-3-2021 t/m 19-03-2021 | 22-3-2021 t/m 26-03-2021 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 19-4-2021 t/m 23-04-2021 | 26-4-2021 t/m 30-04-2021 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 24-5-2021 t/m 29-05-2021 | 31-5-2021 t/m 04-06-2021 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 28-6-2021 t/m 02-07-2021 | 5-7-2021 t/m 30-7-2021 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25
[19 empty] | ma. retro / do. impr. | ma. planning / do. review |  |  |  | ma. retro / do. impr. | ma. planning / do. review |  |  |  | ma. retro / do. review | ma. planning |  |  |  | testweek - geen review | ma plann do retro |  | do review |  |  |  |  | wo och. SG wo mid. planning | ma+wo inh. | ma och. SG ma mid. planning ma+wo inh | ma+wo inh | ma och. SG ma mid. planning ma+wo inh | ma inh wo retro/impr | ma och. SG ma mid. planning ma+wo inh | ma+wo inh | ma och. SG ma mid. planning ma+wo inh | ma inh wo retro/impr
Bellen | 2020-11-09: In welke gemeentelijke processen is ID Bellen van het meest toegevoegde waarde
Video
Chat | 2020-11-09: Welke applicaties worden binnen gemeenteland gebruikt en welke voldoen aan de WDO.
Onderzoek / UX | 2020-11-09: HAN Onderzoek; literatuurstudie over kanaalkeuze van inwoners; 2020-12-07: HAN kwalitatief Onderzoek; literatuurstudie up to date maken met huidige wensen
Techniek | 2020-11-09: Welke applicaties zijn er in de markt beschikbaar en geschikt voor connectie met ID Managers
Communicatie